# 07 | Development Work Plan

Milestones, roles, tasks, tests and evaluation readiness

Version 1.0  |  29 October 2026  |  Status: Proposed / Pre-development

# Execution approach

Recommended delivery: eight milestones over six weeks, with weekly demonstrations. The schedule is an estimate for a small student team and should be adjusted to college deadlines and API approval lead times.

| Period | Milestone | Implementation tasks | Gate / deliverable |
| --- | --- | --- | --- |
| W1 / M1 | Requirements + UX + setup | Freeze PRD, create repo, React/Express scaffolding, error handler, CI test script | App and API health check; reviewed diagrams |
| W1–2 / M2 | Authentication + database | Atlas, models, user CRUD, JWT/cookies, ownership middleware | Login/register tests; user isolation tests |
| W2 / M3 | Dashboard + drafts | Navigation, post CRUD, image URLs, responsive forms | Draft CRUD and validation tests |
| W3 / M4 | AI integration | Prompt templates, AI service, tone picker, error states | Mock API tests; manual AI demonstration |
| W4 / M5 | Scheduling engine | Time validation, target model, durable worker, retry status | Time-zone, duplicate, restart recovery tests |
| W4–5 / M6 | Account/provider connector | Demo adapter first; optional Zernio integration with consent | Fake publishing E2E; real integration proof if permitted |
| W5 / M7 | Analytics + polishing | Status charts, logs, security hardening, responsive UI | Cross-browser, accessibility, security regression |
| W6 / M8 | Deploy + present | Host services, seed demo, prepare report, slides and viva | Deployment smoke test; full demo checklist |

# Prioritized backlog

| Priority | Work items |
| --- | --- |
| P0 / indispensable | Auth, own-data isolation, AI editable draft, post CRUD, date-time scheduling, visible job status, basic tests |
| P1 / strong demo | Dashboard, responsive UI, media references, scheduled worker with crash recovery, demo publishing adapter |
| P2 / external dependency | Actual social account linking, provider publishing, provider analytics, webhooks |
| P3 / enhancement | Multi-user teams, payments, advanced calendar, recommendation engine |

# Suggested team split

| Role | Responsibility |
| --- | --- |
| Frontend developer | React pages, forms, dashboard, integration with API |
| Backend developer | Express routes, security, worker, provider adapter |
| Database/QA/documentation owner | Mongoose models, seed data, tests, diagrams, report |
| Shared responsibility | Reviews, demo rehearsal, API credentials, integration testing |

# Risk register

| Risk | Mitigation |
| --- | --- |
| Social platform API unavailable | Use clearly labeled simulated publishing for the graded MVP |
| AI API spending/quota | Per-user rate limit, request cap and clear failure states |
| Scheduler loses jobs after restart | Persist jobs with claim/lease and retry |
| Unauthorized data access | Ownership test suite and secure route guards |
| Compressed college timeline | Prioritize P0; freeze scope before integration enhancements |

# Definition of done

Code reviewed; tests run green in CI; manual workflow demonstrated.

No secrets in repository; .env.example documented.

Validation and authorization checked for every write endpoint.

Architecture and API docs reflect current code, not aspirational features.

Demo clearly distinguishes simulated from real publishing.

# Next concrete sprint (first 5 working days)

Day 1: confirm scope and Git workflow; set up monorepo; frontend/backend health test.

Day 2: define Mongoose schemas and validation; connect Atlas dev database.

Day 3: write registration/login failing tests and implement authentication.

Day 4: implement protected profile and cross-user authorization tests.

Day 5: create dashboard shell and run end-to-end authentication demo.

# Reference

Reference: GreatStack, “Build an AI Powered Social Media Automation Platform Using MERN Stack | AI Project Tutorial,” published 28 May 2026, https://www.youtube.com/watch?v=L3OmeClSiQ0&t=348s. The public description was used; this package does not claim frame-by-frame verification or reproduce the video source code.